## Gantt Chart
| PROJECT TITLE |  | Web Mining Project (BIA-660) |  |  |  |  | DATE | [6 empty] | 2018-10-30
| PROJECT MEMBERS AND CONTACT |  | Fanyu Wang | fwang15@stevens.edu
|  |  | Kai Zhang | kzhang32@stevens.edu
|  |  | Fu Yang | fyang24@stevens.edu
|  |  | Shuai Wang | swang111@stevens.edu
| WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1. Project Conception and Initiation | 1.1 | Idea Brainstorm | ALL | 2018-09-10 | 2018-09-16 | 7 | 100% | bar: WEEK 1 M to WEEK 1 F
| 1.2 | Project Proposal V1 | Fu Yang | 2018-09-17 | 2018-09-18 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T
| 1.3 | Project Proposal Update | Fu Yang | 2018-09-18 | 2018-09-19 | 2 | 100% | bar: WEEK 2 T to WEEK 2 W
| 1.4 | Meet Prof. | ALL | 2018-09-20 | 2018-09-20 | 1 | 100% | bar: WEEK 2 R
| 1.5 | Project Idea Confirmation | ALL | 2018-09-20 | 2018-09-21 | 2 | 100% | bar: WEEK 2 R to WEEK 2 F
| 1.6 | Project Initiation | ALL | 2018-09-24 | 2018-09-24 | 1 | 100% | bar: WEEK 3 M
| 1.7 | Project Plan | Fu Yang | 2018-09-24 | 2018-09-25 | 2 | 100% | bar: WEEK 3 M to WEEK 3 T
2. Project Launch and Execution | 2.1 | Tech Research(Suitable for Steam platform) | Kai Zhang, Fanyu Wang | 2019-10-03 | 2019-10-05 | 3 | 100% | bar: WEEK 4 W to WEEK 4 F
| 2.2 | Steam Platform Research | ALL | 2019-10-11 | 2019-10-17 | 5 | 100% | bar: WEEK 5 R to WEEK 6 W
| 2.3 | Scrape data from Steam platform | Shuai Wang | 2019-10-19 | 2019-10-24 | 4 | 100% | bar: WEEK 6 F to WEEK 7 W
| 2.4 | Group Meeting | ALL | 2019-10-25 | 2019-10-25 | 1 | 100% | bar: WEEK 7 R
| 2.5 | Data Tokenization and normalization | Fanyu Wang | 2019-10-24 | 2019-10-26 | 3 | 100% | bar: WEEK 7 W to WEEK 7 F
| 2.6 | Group Meeting | ALL | 2019-10-31 | 2019-10-31 | 1 | 100% | bar: WEEK 8 W
| 2.7 | Data scrubbing | Kai Zhang | 2019-10-30 | 2019-11-01 | 2 | 100% | bar: WEEK 8 M to WEEK 8 W
| 2.8 | EDA: Sentiment Analytics | Fu Yang | 2019-10-29 | 2019-10-31 | 2 | 100%
| 2.9 | EDA: Find variable relations | Fu Yang | 2019-10-30 | 2019-11-01 | 2 | 100%
| 2.1 | Mid-term Script Writing | Kai Zhang | 2019-10-31 | 2019-11-01 | 2 | 100%
| 2.11 | Mid-term Plan | Fu Yang | 2019-10-31 | 2019-11-01 | 1 | 100% | bar: WEEK 8 M to WEEK 8 R
3. Further Work | 4.1 | Further explore | TBC |  |  |  | 0%
| 4.2 | Colleration analysis: e.g. between high helpful reviews | TBC
| 4.3 | Text analysis based on clustering | TBC
| 4.4 | Mearching Learing: Find high 'helpful' review | TBC
| 4.1 | Final Project Report and Presentation | ALL | 2018-12-06 | 2018-12-06 | 1 | 0%